## Sheet1
Checklist | Example Tasks | Timeline
Planning stage
Site Visit
Determine control lines (GPS)
Record vegetation/ fuel types
Establish access routes
Communications at site (Cell, land line, etc)
Landing Zones (GPS)
Burn Task Checklist
Burn Plan
Maps
Prescription (i.e. Behave Modeling)
Medical plan
Burn goals
Outline Weather windows
Local weather stations (RAWS)
Historical weather data
Smoke Management Plan or Other Permitting
Emissions calculations
CAL FIRE outreach
Early resource outreach
Local Fire Departments, Burn Bosses, Agencies, Key Volunteers
Media Plan (optional)
Identify media outlets
Media strategy
Monitoring (optional)
Monitoring objectives
Monitoring methods
Plot locations and materials
Communications
Methods for neighbor outreach
Social media plan (optional)
Local media outlets (optional)
Nixle, etc (optional)
Media liasion (optional)
Preparation Stage
Weather watch for burn window
Resource request
Resource requirements via Burn Plan
Reach Out to Potential Resources
*Example: PBA volunteers, Volunteer FD's equipment
Incident Action Plan
Detailed prep list
*Example: clear road, set up porta-tank, clear lines
Hose lays (optional)
Hose/Brass Requirements
Water Source for Hoselay (eg. Portatank/Engine)
Gear prep
Make gear list and procurement
*Example: drip mix, pumps, radios, PPE
Air Qual weather/ notification
Call For Forecast
Spot weather observations (optional)
Seed collection/ Monitoring (optional)
Weed Concerns and Mitigation
Native Plants Seed Locations
Traffic notifications (optional)
CHP, Cal Trans, Sheriff
How many "Rx fire" signs?
Press release/ Media invite
Invite Observers
Food prep
Make list and purchase of food for burn
*Example: bag lunches, snax, drinks, post fire party
Parking prep
Parking, Staging Areas, Carpool
Printing
*Example: IAP, Briefing maps, Liability waivers, Burn plan
Neighbor notification
Social media notification (optional)
NextDoor, Facebook, Twitter
Burn management check-in
Day before with: Land owner, PBA organizers, Burn/ Holding/ Firing Boss
Spot Forecast
Request from NWS for safety forecast
Day of Burn
Burn site signage
Directions to burn site
"Rx Fire Ahead" signs set up
Parking coordinator (optional)
Check in station (optional)
Check in volunteers for gear and waivers
Food station (optional)
Set up sandwich making table (lunch)
Agency notifications
CAL FIRE, Fire Districts, Air Quality, Dispatch
Media liaison (optional)
Observer liaison (optional)
Observation Locations
Morning briefing
Management Roles | *Example:
Land owner rep.
Burn boss
"Burn organizer"
Firing boss
Firing holding
Crew boss
Fire weather
Medical/ EMTs
After party/ BBQ prep (optional?)
Mop up
Day of mop up
Air Qual completion notification
Check in/ pack up gear
Remove "Rx Fire" signs
Hose lay clean up (optional)
Evening of burn monitor
Days after monitor
Day after mop up
Thank you emails
Social media posts (optional)
Wash PPE
Clean tools, organize and put away

## Tool Check List
Prescribed burn signs